## Timeline
Project Phase | Tentative Dates | Updated Tentative Dates | Teams
Requirement Gathering | 6/2/25-6/13/25 | 6/2/25-6/13/25 | HRIS/IT/Benefits
Development Build / Unit Testing | 6/16/25- 8/1/25 | 6/16/25- 09/12/25 | HRIS/IT
HRIS Testing | 7/1/25- 8/1/25 | 7/1/25- 9/26/25 | HRIS/IT
User Unit Testing | 8/4/25-8/15/25 | 09/29/25 - 10/10/25 | Benefits/HRIS
UAT User Testing | 8/25/25 - 9/19/25 | 10/13/25 - 10/24/25 | Benefits/HRIS
Documents review for Go Live | 9/16/25 - 9/30/25 | 10/27/25 - 11/07/25 | HRIS/IT
Prod move | 12/30/25 - 1/4/26 | 12/30/25 - 1/4/26 | IT/HRIS
Objects | ETA | Resource | Status | 7.19.25 | 08.12.2025 | 08.19.2025 | 08.26.2025 | 09.02.2025 | 09.09.2025 | 09.16.2025 | 09.22.2025 | 09.30.2025 | 10.21.2025 | 10.28.2025 | 11.11.2025
Extract - Business Report Mode: OIC Flow name: Note: To be scheduled post go-live - files to be places on shared network drive. | 09.12.2025 | Anu | Completed. Anu to verify variances | Extract complete. Navya sent back test results | PJ - Reported few issues on report. Anu is working on and Eligibility changes for CPM and NCPM | PJ - Reported few issues on report. Anu is working on and Eligibility changes for CPM and NCPM | Currently working on OIC approach for Report. Date to be provided by Anu tomorrow (08.27) | Currently working on OIC approach for Report. ETA :09.05 - Anu to add selection criteria to the extract based on Ravindr's logic OIC: ETA: 09.03.2025- Ravindr completed Development and yet to test data. Venu to provide file path with Anu. | Anu shared extract and observed 3 records have incorrect Social Security wages. Anu is waiting for Ravindr to complete OIC part. Requested filters: Age 50 or above and No IC TRU's | Removed Element entries(Percentage) from extract to increase and test run time - Current Run time is 1:05 hrs | Extract completed, waiting for Patrick's part to complete and generate final files. | Shared by Anu. 4 records displayed incorrect Social security wages Anu to check those differences. | Anu -Researching incorrect social security wage records. | Melisaa provided folder and IT to work with THRU for automatically placing file on network drive
Unit Test Extract Data | 09.12.2025 | Navya | Completed | Completed, file uplaoded to Sharepoint | [6 empty] | Waiting for final files to test and validate | Completed and sent to HRIS | Test data looks good except 4 off records. validating 401K percentages
Review Extract Data | 09.12.2025 | PJ | Completed | In progress |  |  | reviewed and sent back for data issues |  |  |  | Waiting for final files to test and validate |  | Test data looks good except 4 off records. validating 401K percentages
Run HDL to upload data IT to upload HDL file onto SharePoint folder Path: | 10.03.2025 | PJ |  | In progress |  |  |  | OIC: ETA: 09.03.2025- Ravindr completed Development and yet to test data. Venu to provide file path with Anu. | WIP | Patrick to generate HDL file from extract and will share with HRIS team by 09.19 | Waiting for final files to test and validate | Anu to update HDL effective date to start of the year. | Anu updated HDL effective date critieria to pick year start date.
Validate HDL data from extract | 10.03.2025 | Ravindr | Expected to complete in 2 weeks | In progress |  |  |  |  | WIP |  | Waiting for final files to test and validate | HDL data is validated and test loader for 1 EE. will update effective date and load CalculationCard. | Anu updated HDL effective date critieria to pick year start date.
Validate Data if imported all records correctly | 10.03.2025 | Navya |  | In progress | [6 empty] | Waiting for final files to test and validate
Review HDL Data | 9.30.2025 | PJ | Completed | In progress | [5 empty] | Waiting for HDL file to review after unit testing is completed by IT. | Waiting for final files to test and validate
Run payroll | 10.10.2025 | PJ |  | In progress | [5 empty] | Waiting for HDL file to review after unit testing is completed by IT. |  | WIP | BWFri1 payroll is run and HRIS shared analysis with business
401k FF , 401k Roth FF | 10.10.2025 | Joel | FF is complete, Unit testing is complete. Waiting for all other scenarios to complete and payroll run is pending. | In progress | Requested Joel to create UDT for business to have control on the limit |  | Testing in progress: Business requested UDT for limit | Testing in progress. Complex scenarios were tested and evidences uploaded. |  |  | Currently in progress | WIP | BWFri1 payroll is run and HRIS shared analysis with business
New Extract - Full File- to load new input value Mode: Oracle Flow name: | 2025-09-05 | Anu | Testing In Progress | Yet to start development |  |  | Anu shared report. Testing in progress | Anu shared report. Testing in progress | Anu shared report. Testing in progress |  |  | Anu to share details | Anu to schedule a call tomorrow 10.22. to discuss latest changes. | Anu fixed the issues and PJ to review - 10.28.25
New Extract changes only - to load new input value Mode: Oracle Flow name: | 2025-09-05 | Anu | Testing In Progress | Yet to start development |  |  | Anu shared report. Testing in progress | Anu shared report. Testing in progress | Anu shared report. Testing in progress |  |  | Anu to share details | Anu to schedule a call tomorrow 10.22. to discuss latest changes. | Anu to complete development by 10.31.25
Notes:
08.05.25
If HDL is successful for EE with final close date, extract will include all active and terminated ee of previous year.
2025-09-16
Test HDL load for Inactive EE in 2025 (elig wages in 2024)
10.21.2025:
If incorrect social security wages issue is not fixed, we'll have to manually validate and fix the incorrect records flag status

## YE-YB Process
Process Sequence | Flow Name | Resource | Prod Migartion | Prod - Run time | Dev4 timing | Dev4 2026 timing | Comments | Process run time | Prod Move
OIC flow for Business report with 401k element entries for all Employees | EVHC_PAY259_BEN_SS_WAGES_SECURE_GEN_CSV (Here select Input Parameter Effective Date =2025 and Type = CSV) | Anu | 2025-12-19 | 1/2/2026 - 9 AM CT | 2025-11-03 | Complete |  |  | 12/31/25 - Once payrolls for 2025 are closed
Flow completes and file is placed on Share point/ network drive |  | Anu |  | 1/2/2026 - 9AM CST | 2025-11-05 | Complete |  |  | 2025-12-31
IT to validate data for Reports and HDL |  | Anu/Navya/Patrick |  | 1/2/2026 - 11 AM CST |  | Complete
Review Report by HRIS/ Business for emp eligibility for secure 2.0 |  | PJ/Ramya/Melissa |  | 1/2/2026 - EOD | 2025-11-05 | 2025-11-18 |  |  | 2026-01-02
OIC flow to update Secure 2.0 Flag on Reporting information - HDL | EVHC_PAY259_BEN_SS_WAGES_SECURE_SCH | Anu | 2025-12-19 | 1/2/2026 - 1 PM CST | Complete | 2025-11-19
Flow completes and file is placed on Share point |  | Anu |  | 2026-01-02 | Complete | 2025-11-19
Manual HDL Load |  | PJ/Ramya |  | 2026-01-03 | Complete | 2025-11-19 |  |  | 2026-01-02
HDL errors review |  | Anu |  | 2026-01-03
Review HDL Load |  | PJ/Ramya |  | 2026-01-03 | Complete | 2025-11-19 |  |  | 2026-01-02
Eligibility Extract Report | EVHC_PAY259_SECURE2_INPUT_VALUE_ENTRY_REPORT | Anu | 2025-12-19 |  | Complete | 2025-11-19 | Dev19 Flow went to error |  | 2026-01-02
Eligibility Extract Review : Run Report for all eligible emps for secure input value update |  | PJ/Ramya/Melissa |  | 2026-01-03
Run Yearly HDL Load | EVHC_PAY259_SECURE2_INPUT_VALUE_ENTRY_HDL | Anu/Navya | 2025-12-19 |  | Complete | 2025-11-19 | Add success report to flow
Run Yearly HDL Load secure input value update in Debug mode |  | PJ/Ramya |  | 2026-01-03 | Complete | 2025-11-19
Eligibility Extract Review : Run Report for all eligible emps for secure input value update | EVHC_PAY259_SECURE2_INPUT_VALUE_ENTRY_REPORT | PJ/Ramya/Melissa | 2025-12-19 | 2026-01-03 | Complete | 2025-11-19 |  |  | 2026-01-02
401K FF Code | Update FF names | Joel | 2026-01-02 | 1/2/26 - To be completed by 12 NOON CST COMPLETED - JSJOHNSON - 11:30 AM CST
Run Payrolls | [5 empty] | 2025-12-11
Run Integration 149 |  | Anu/navya/patrick |  | 1/2/2026 AT NOON ct |  |  | MW to send file after payroll run to test 149 and Extract 2 changes only
Integration 149 schedule change |  | Navya / Melissa |  | Melissa to confirm
Extract 2 - Changes only | EVHC Secure 2.0 Changes Load FF used in above flow :EVHC_SECURE2_ELIG_PRETAX_ELEMENT_ENTRY | Navya | 2025-12-19 | Only start scheduling from 1/9/25 - 1 hour after 149 Integration | 2025-11-20 |  | 11.18: After FF changes, Melissa to validate and confirm
Extract 2 - THRU Config | FTP Folder : PAY_IFI_259_SECURE2.0 |  | 2026-01-06
IT to review changes only file |  | Anu/Navya |  |  | 2025-11-20 |  | 11.18: After FF changes, Melissa to validate and confirm
Extract 2 Changes only - To be scheduled in OIC | EVHC_PAY_IFI_259_SECURE2_CHANGESONLY_SCH Lookups : EVHC_Inbound_Intg_Metadata_Lookup,EVHC_HCM_Inbound_Email_LKP,ENV_PAY_Email_Notification_LK | Navya/Patrcik | 2025-12-19 | Only start scheduling from 1/9/25 - 1 hour after 149 Integration | Complete
Value sets | ENV_GET_259_CHANGESONLY_ASG_VS ENV_GET_SSW_ELIG_FLAG_CHGONLY_VS | Anu |  |  |  |  | Added here on1.8.2026
Extract 2 Changes only - HRIS Review |  | PJ/Ramya/melissa |  | 2026-01-12 | 2025-11-20 |  | 11.18: After FF changes, Melissa to validate and confirm
Extract 2 - Test load |  | PJ/Ramya |  |  | 2025-11-20 |  | 11.18: After FF changes, Melissa to validate and confirm
UDT: ENV_PAY_401K_SECURE2_UDT |  |  | 2026-01-02 | 1/2/26 - To be completed by 12 NOON CST COMPLETED - PJ - 10:30 AM CST
Change Input Value Name - Goal Amount |  |  | 2026-01-02 | 1/2/26 - To be completed by 12 NOON CST COMPLETED - PJ - 10:30 AM CST

## Logic for IT
| Condition |  | Report
Eligibility | Employees with Wages >145000 by TRU in previous year for Non CPM PSU Employees with Wages >145000 by TRU in previous year for CPM PSU If Federal Tax Limit Enforcement Level = Tax reporting Unit then that TRU is on NON CPM PSU |  | Person Number,Payroll Relationship Number, Legal Employer, Common PayMaster (Yes/No),Tax Reporting Unit, Payroll Statutory Unit, Age,Eligibility flag, Exceeded Limit ( Yes/ No), SS Wages for prev year(Social security reduced subject withholding), Prev Year
If eligility is Yes, then Only 401K Roth Catch
Element Addition / Deletion | 1- Employees with Wages >145000 by TRU in previous year for CPM PSU & eligiblity - Yes Skip 401k catch up 2-Employees with Wages >145000 by TRU in previous year for Non CPM PSU & eligibility - Yes, for those TRU's - only 401k Roth catch up should be deducted & logic should be changed such that deduction limit should consider only for eligible TRUs. 401k Catch up should not be deducted 2a - if all TRU's in non CPM for that employee have eligibility - Yes, then skip 401k catch up for both of above!
Adding 401K Roth Catch up | If 401k roth catcup is not added to employee, it should be added manually by benefits team.
Attach to eligible employees | Check Oracle doc for HDL | https://docs.oracle.com/en/cloud/saas/human-resources/25b/falzi/eligibility-for-pretax-catch-up-contributions-for-deferred-compensation-plans.html#Opt-out-individual-employees
Add DB item to get eligibility and add to FF | Check Oracle doc for DB Item | ORA_HRX_US_REP_CARD_ELIGIBLE_PRETAX_CATCHUP
FF Changes | Depending on TRU ( NON CPM PSU or CPM PSU) & eligibility , We have use approriate Wages to calculate on existing 401k Catch up
FF Changes for percentage | Add input values - percentage & Additional Percentage - Secure 2.0 to get the 401k roth catch up percentage
IT Design:
Payroll flow
report to pick eligible employee | Include validate step ( manual stop) in the flow
HDL Load | For CPM: If sum of SS Reduced sub wh of all TRu's of that Payroll Rel crosses 145000, we need to turn flag on. For NCPM: We need to determine by TRU wages (SS reduced sub wh, If any of the TRU wages crosses 145k, that payroll rel is eligible.
report for hdl load status
Extract to update new input value percentage of 401k roth catch up element with 401k catch up percentage
Fast formula - calculate values based on eligible logic and hdl
call this FF to existing FF ( 401k roth catch up, 401K catch up)
FF on percentage
Dev11
Pretax only example - EE has only pretax election. For entities in which wage threshold was met in prior year, the 10% pretax will need to be automatically directed to the Roth Catchup.
This is for new year - In current case - its 2026
For Non CPM PSU- TRUs | Employee Deferral % (Election at Fidelity) | wages | Pretax 401K Contrib | 401K Roth Contrib | 401k Catch up - pretax % | 401k catch up - pretax deduction | 401k roth catch up% | 401k roth catch up - deduction
Arizona Perinatal Care Centers LLC - Eligible | 10% Pretax/0% 401K Roth | 10000 | 1000 | 0 | 10 | 0 | 10 | 1000
Sheridan Healthcare Inc. - Not eligible | 10% Pretax/0% 401K Roth | 20000 | 2000 | 0 | 10 | 2000 | 0 | 0
Pretax & Roth 401k example - 5% - pretax and 5% - Roth = under entity where wage threshold was met, total Roth percentage should be 10% to account for both "5%'s"
For Non CPM PSU- TRUs | Employee Deferral % (Election at Fidelity) | wages | Pretax 401K Contrib | 401K Roth Contrib | 401k Catch up - pretax % | 401k catch up - pretax deduction | 401k roth catch up% | 401k roth catch up - deduction
Arizona Perinatal Care Centers LLC - Eligible | 5% Pretax/5% 401K Roth | 10000 | 500 | 500 | 5 | 0 | 10 | 1000
Sheridan Healthcare Inc. - Not eligible | 5% Pretax/5% 401K Roth | 20000 | 1000 | 1000 | 5 | 500 | 5 | 500
Roth 401k only example - EE has only Roth 401k election. For entities in which wage threshold was met in prior year, the 10% Roth election will hold across all entities.
For Non CPM PSU- TRUs | Employee Deferral % (Election at Fidelity) | wages | Pretax 401K Contrib | 401K Roth Contrib | 401k Catch up - pretax % | 401k catch up - pretax deduction | 401k roth catch up% | 401k roth catch up - deduction
Arizona Perinatal Care Centers LLC - Eligible | 0% Pretax/10% 401K Roth | 10000 | 0 | 1000 | 0 | 0 | 10 | 1000
Sheridan Healthcare Inc. - Not eligible | 0% Pretax/10% 401K Roth | 20000 | 0 | 2000 | 0 | 0 | 10 | 2000
HRIS Questions
How do we handle election changes through out the new year | example on Row 108 - if employee chooses to start his pretax , then what would be roth % ?
How do we handle election changes through out the new year | example on Row 101 - if employee chooses to change his pretax , then what would be roth % ?
do you want visibility to roth catch up% for TRU that are eliglible and have pre and post tax elements | Example on rows 101,102
| Current Percentage | Additional Percentage - Secure 2.0 | Total Percentage for calculation
401k CATCH UP | 10 | NA | 0
401k roth catch up | 5 | 10 | 15

## Report
[11 empty] | Percentages from Element entries |  |  |  | TBD | Important consideration for extract
Person Number | Payroll Relationship Number | Legal Employer | Common PayMaster (Yes/No) | Tax Reporting Unit | Payroll Statutory Unit | Age( As of 12/31/2025) | Eligibility flag | Exceeded Limit ( Yes/ No) | SS Wages for prev year(Social security reduced subject withholding) | Prev Year | 401K Pretax | 401K Catch-up | 401K Roth | 401K Roth Catch-up | Secure 2.0 Prcentage | Effective date of the report (paramater): 01.01.2026
20557254 | 20557254 | Greater Florida Anesthesiologists LLC | No | Greater Florida Anesthesiologists LLC(27-0602251) | Envision Physician Services, LLC | 53 | Yes | Yes | 539393.4 | 2024 | 10 |  |  | 10 | 0 | Dates to check wages: Effective date year - 1, so it will be 2025 wages in this case.
20219274 | 20219274 | Morristown Emergency Medical Associates LLC | Yes | Morristown Emergency Medical Associates LLC(26-4467460) | Emergency Medical Associates of New Jersey PA | 50 | Yes | Yes | 374657.43 | 2024 |  |  |  |  | 0 | Element entries: to check as of sys date.
7018 | 7018 | Jupiter Anesthesia Associates L.L.C. | No | Jupiter Anesthesia Associates L.L.C. | Envision Physician Services, LLC | 65 | Yes | Yes | 270434.52 | 2024 |  |  |  |  | 0
0
EE in both Common/NonCPM | [14 empty] | 0
10548 | 10548 | Lawnwood Anesthesia Providers, LLC(85-2310942) | No | Lawnwood Anesthesia Providers, LLC | FL-I Medical Services LLC | 67 | Yes | Yes | 215510.2 | 2024 |  |  |  |  | 0
10548 | 10548-1 | Anesthesia Physician Solutions of South Florida LLC(46-4364900) | Yes | Anesthesia Physician Solutions of South Florida LLC | HCA-Sheridan Holdings LLC | 67 | Yes | Yes | 222556.87 | 2024 |  |  |  |  | 0
0
227380 | 227380-1 | Kentucky EM-I Medical Services(75-2772210) | No | Kentucky EM-I Medical Services(75-2772210) | Envision Physician Services, LLC | 57 | Yes | Yes | 219409.61 | 2024 |  |  |  |  | 0
227380 | 227380 |  | Yes | Emergency Care Physicians of Washington LLC(26-2315767) | New Jersey/Penn EM-I Medical Services | 57 | Yes | Yes | 149974.98 | 2024 |  |  |  |  | 0
|  | Emergency Care Physicians of Washington LLC(26-2315767) | [12 empty] | 0
Not Eligible | [14 empty] | 0
20129196 |  | Velasco Inpatient Services PLLC(27-4976722) | Yes | Velasco Inpatient Services PLLC(27-4976722) | Inpatient Services of Texas | 51 | No | No | 142604.99 | 2024 |  |  |  |  | 0