## Sequence
USOPTE Testing steps - Test POD Dev11 ( refreshed as of 6.30.25) | Responsibility |  | Timeline
Tasks & Activities | Envision | AMS
Planning
Identify environment to perform testing | X
Schedule P2T | X
Regression Testing |  |  | 8/6/25 - 8/22/25
Identify Payrolls to Run ( all payrolls) | X
Stage Time Data | X |  | 2025-08-08
Run Payroll on Vertex tax engine (Base Line) |  | X | 8/11/25 - 8/22/25
Config PRT tool in Dev 11 |  | X
Run Payroll Calculation Flow for all Payrolls |  | X
Run the following payroll run reports needed for comparison - |  | X
Gross-to-Net-Report |  | X
Periodic Statutory Deduction Register (run in Detail mode) |  | X
Periodic Payroll Activity Report (run in Detail mode) |  | X
Element Results register report (run in detail mode)
Run Employee Active Payroll Balance Reports |  | X
Federal run balances |  | X
State run balances |  | X
Local run balances |  | X
Calc Cards - Federal, State, Local , SD, PSD (Run Tax Withholding Card Audit Report) | X
Validate all reports have been run and captured |  | X
Prepayments , reports for prepayments , Archive, EFT, Check payments, TP EFT, TP Check payments, Payslip |  | X
Third party Periodic ( Quarter begin - check date) , Third party Monthly, Third party Quarterly |  | X
Run Baseline PRT extracts |  | X
Roll Back all payroll processes |  | X
Address Validation Enablement & Process |  |  | 8/25/2025 - 9/19/25
Enable Enhanced Address Validation for US features
Run Address Validation Process Flow | X
Review invalid or partially validated addresses | X | X
Inform HRBPs/ Payroll/ Change Mangement/ Employees regarding address changes | X
Correct address at source (Production and Test) ( this will happen later in the year after contacting emps) | X
Rerun the process in final mode to commit changes | X
Enable Redwood Profile - ORA_PAY_CALC_ENTRIES_LANDING_REDWOOD_ENABLED | X
Run Sync Cal Cards for US - Local and Pennsylvania PSD
US OPTE Transition Review - Steps | X | X | 9/8/2025-9/11/2025
Payroll Tax Enablement & Validation Process |  |  | 9/11/25 - 9/30/25
Enable USOPTE
Run Diagnostic Test |  | X
Enable the Oracle tax engine |  | X
Validate the Oracle tax engine has been enabled |  | X
Set earnings accumulation transition date - Based on previous payroll Earned date with Vertex *Run RPT018 BI Report and confirm last pay period to determine Earnings accumulation date | X
Run Tax Withholding Audit Report flow to verify changes | X
Run the payroll on USOPTE |  | X
Run Payroll Calculation for the following payroll(s) |  | X
Run the following payroll run reports needed for comparison |  | X
Gross-to-Net-Report |  | X
Periodic Statutory Deduction Register (run in Detail mode) |  | X
Periodic Payroll Activity Report (run in Detail mode) |  | X
Element Results register report (run in detail mode)
Run Periodic Payroll Register Report
Run Employee Active Payroll Balance Report |  | X
Federal run balances |  | X
State run balances |  | X
Local run balances |  | X
Calc Cards - Federal, State, Local , SD, PSD (Run Tax Withholding Card Audit Report) | X
Prepayments , reports for prepayments , Archive, EFT, Check payments, TP EFT, TP Check payments, Payslip |  | X
Run Baseline PRT extracts |  | X
Third party Periodic ( Quarter begin - check date) , Third party Monthly, Third party Quarterly |  | X
Review Payroll Results | X | X | 9/22/25 - 9/30/25
Payroll Reconciliation Testing ( Tax Team) |  |  | 10/1/25 - 10/30/25
Compare Vertex to USOPTE Payroll Calculation Results
Compare the Vertex payroll tax engine results against the USOPTE results | X | X
Compare the Vertex payroll tax engine results against the USOPTE results using PRT tool
Review Compare Results & Identify Differences | X | X
Open SR if needed | X | X
Research & Resolve Differences | X | X
Review Custom FF's | X | X
Deploy |  |  | Jan2025 - before First payroll run - BWfri ( check date 1/9/25)
Enable Enhanced Address Validation for US features in Production | X
Run Address Validation Process to Validate and Update Home and Work Addresses | X
Enable USOPTE (Tax Engine) | X

## Test - Pay Periods
Calendar Week | Payroll ID | Period Start | Period End | Payroll INPUT Due from Scheduling | Payroll INPUT Due from Finance/WFO | Time Due | Processing Open Date | Processing Close Date | Pay Date | Notes
28 | M10 | 2025-06-01 | 2025-06-30 | 2025-07-01 | 2025-07-02 | End of Day | Thursday, July 3, 2025 | Monday, July 7, 2025 | Thursday, July 10, 2025 | Accelerated processing - Holiday
28 | SM1025 | 2025-06-16 | 2025-06-30 | 2025-07-02 | 2025-07-03 | 10:00AM Eastern | Thursday, July 3, 2025 | Monday, July 7, 2025 | Thursday, July 10, 2025 | Accelerated processing - Holiday
28 | BWFRI1 | 2025-06-22 | 2025-07-05 | 2025-07-07 | 2025-07-06 | 10:00AM Eastern | Monday, July 7, 2025 | Wednesday, July 9, 2025 | Friday, July 11, 2025
28 | EXBW1 | 2025-06-22 | 2025-07-05 |  |  |  | Tuesday, July 8, 2025 | Wednesday, July 9, 2025 | Friday, July 11, 2025
29 | M15 | 2025-06-01 | 2025-06-30 | 2025-07-07 | 2025-07-10 | 5:00PM Eastern | Thursday, July 10, 2025 | Friday, July 11, 2025 | Tuesday, July 15, 2025
29 | SM15EOM | 2025-06-16 | 2025-06-30 | 2025-07-03 | 2025-07-07 | 5:00PM Eastern | Thursday, July 10, 2025 | Friday, July 11, 2025 | Tuesday, July 15, 2025
29 | M20 | 2025-06-01 | 2025-06-30 | 2025-07-08 | 2024-07-14 | 5:00PM Eastern | Tuesday, July 15, 2025 | Wednesday, July 16, 2025 | Friday, July 18, 2025
31 | MEOM | 2025-06-01 | 2025-06-30 | 2025-07-18 | 2025-07-23 | 5:00PM Eastern | Monday, July 28, 2025 | Tuesday, July 29, 2025 | Thursday, July 31, 2025